### 30th September 2022

- Presentation rescheduled to 5th October - Pratik will pre-record and share

  - Flow -

    - Pratik + Malav (Intro)

    - Jisan (DS - Past)

    - Harriet (DS - This sem)

    - Gautam (UX)

    - Ankit + Ritika (Web-dev)

    - Conclusion (Pratik)

- VIP notebooks on github + Peer-evaluations coming up

- VIP competition?

- Access to data

Deliverables:

- - Malav

- Complete preprocessing for text data for Aspect-based sentiment - Jisan

- Generating the csv output for sharing with Web-dev team - Harriet

- - Gautam

- Create the grid layout in React for the remaining pages of wireframe - Ankit

- - Ritika

- Record your presentation bits - Pratik

- - Kimaya

### 23rd September 2022

- Presentation rescheduled to 5th October - Pratik will pre-record and share

- VIP notebooks on github + Peer-evaluations coming up

- VIP competition?

- Access to data

Deliverables:

- Implement the PAM, NMF. Create the 1-pager of analysis of models and findings - Malav

- Work with Harriet, reflect on comparative advantage, and divide the implementation bits - Jisan

- Write code adapted to Piazza data if the keyword mismatch issue is sorted - Harriet

- Working with graphs in React grid layout created by Ankit and Ritika - Gautam

- Create the grid layout in React for the second page of wireframe - Ankit

- Create react components and experiment locally + assist Gautam to translate the wireframes to working components - Ritika

- Help Harriet and Jisan if required with the Aspect-Based SA problem, record your presentation bits - Pratik

- Just be available if help is needed, slack/teams - Kimaya

### 16th September 2022

- Data forms

  - Does everyone need to fill again or only the new members?

  - Any new data?

- Reflections for the journal club presentation (21st September)

- Presentation (28th September)

  - Could interfere with CS Career fair, so alternatives to be explored

  - Pratik to share the template by 21st, slides to be completed by 26th

- Github notebooks

- Progress

Deliverables:

- Create a 1-pager for comparative understanding of the models you’re evaluating and share findings - Malav

  - Reading about topic modeling, PAM, NMF => DAGs

- Find and test 1 implementation of Aspect-based sentiment analysis on our data - Jisan

- Test 1 implementation of Aspect-based sentiment analysis - Harriet

  - Tested the implementation, works on the source data, doesn’t directly work on our Piazza data due to mismatching keywords

    - To look deeper into the code, where is it sourcing keywords.

- Create a plan for distributing front-end work, update Ankit and Ritika on call with James - Gautam

  - Front page of dashboard (~looks like Figma, still can be improved)

- Connect and understand existing code, go through the previous semester presentation and share your understanding next week - Ankit

  - Grid layout in React, make it look like the Figma layout

- Connect and understand existing code, go through the previous semester presentation and share your understanding next week - Ritika

  - Connected with Gautam, started working on React components

- Share the template presentation, help out Jisan and Malav if required, and share resources for React (if required) - Pratik

- Get back on any new data, permissions and presentation dates - Kimaya

### 9th September 2022

- Team intros

  - Ankit: Junior CS, interested in online learning env., volunteer teacher in Nepal. Learning React, working front-end

  - Gautam: React, dashboard

  - Harriet: CS, web-dev -> data science

  - Jisan: CS, data science team, topic-modeling -> aspect-based sentiment modeling

  - Kimaya: First year MS-CS, GRA, TA for this class. C21U - Dr. Lee

  - Malav: CS, Math (minor), Data Science

  - Pratik: MS-CS completed, Project manager

  - Ritika: CS, front-end, learning react

- Access to resources

  - Github

  - Slack

  - Gdrive

- Aspect-based sentiment, cognitive presence, topic-modeling

Deliverables:

- Rerun models from previous semesters - Malav

- Find multiple implementations of Aspect-based sentiment analysis - Jisan

- Create a 1-pager guide for future members based on your understanding + help run models with Malav’s help - Harriet

- Get the intro page same as the mockup + Call with James - Gautam

- Help Gautam on the react intro page - Ankit

- Help Gautam on the react intro page, get familiar with React - Ritika

- Create the poll for Journal club, coordinate team on the presentation, setup meeting with James - Pratik

- Confirm about the ppt - Kimaya