Presentation 1

- Design document

  - Having specific research questions

- Data science

  - Rough plan without too much detail

  - Having an initial model

  - Idea of the pipeline

  - Distribute reading of papers

- Web development

  - Very basic back end

  - Database with dummy data

March 10th (2 weeks)

- Design document

  - First draft

- Data science

  - Play with current data

  - Look at the libraries for feature extraction

  - Ideally work in Python

  - Set up the environment (if David gets his computer)

  - Simulation experiment

- Web development

  - Implement ideas from database to front-end

  - Database: look through Piazza and edX data, convert it into a model we can use with SQLAlchemy

  - Front-end: continue with more iterations of wireframes

    - Initial high-fidelity designs?

March 31st (2 weeks)

- David (DS)

  - Generate mock data files

  - Discussion Context Feature

  - LIWC

  - Set up training/validation split

  - Add Random Forest Model

- Nidhi - get a rough draft of the rest of the visualizations from kabir paper that are applicable as well as the other ideas I had

- Aanya

  - Get access and understand the EdX and Piazza data

  - Create a model for the database

  - Implement a connection between the database

April 14th (2 weeks)

- Aanya

  - Connect real frontend to application

  - Finalise backend

  - Create database structure

  - Pass data through pipeline

- Nidhi

  - Create visualizations based on the survey responses

  - Get the updated Piazza data from the database/file

  - Get edX data set up for metrics such as “cognitive presence by user” and “are some users never active?” because it has unique identifiers

- David

  - Get LIWC 2015 functional

  - Finish Discussion Context Features

  - Implement RF model

  - Graph confusion matrix

- Pratik

  - Model experimentation with BERT

  - Read Papers shared by Dr. Joyner and more on Generative models for social network analysis

  - Extend analysis on the comments network

- Sambhav

  - Translate wireframes to React

  - Experiment with data visualization libraries

  - Get data visualization onto website

- Morgan

  - Update design document with innovation competition information

  - Create new Google form with visualizations for more input

  - Schedule meeting with Dr. Joyner (?)

    - Possibly for next semester

    - If this happens this semester, I will create an agenda with questions we have

    - Should probably read the papers he gave us before we meet with him

- Everyone

  - Look through survey responses

  - Continue to send it out to other professors/TAs

  - Read Dr. Joyner’s recommended papers

April 28th (2 weeks)

- Everyone

  - Final presentation

- Morgan

  - Finalize design document for next semester’s team

- Aanya

  - Meet and take feedback from Dr. Joyner

  - Coordinate with Data science and front-end about how to model data

  - Collect more information about the requirements and needs from the database

  - Final Presentation

- David

  - Implement RF model

  - Graph confusion matrix

  - Presentation Slides

- Pratik

  - Wrap-up BERT prediction model

  - Apply LIME framework on the comments

  - Show change in cognitive presence over time?

  - Social media analysis and problem statement for next sem

  - Finalize code, create web-app integration, talk to Sambhav+Aanya

- Nidhi

  - Create dummy data regarding participation and for other data we don’t have

  - Coordinate with Sambhav to add the metrics from the survey to the front end

  - Talk to more professors and TAs outside of CS

  - Presentation slides